## Trust Fund Utilization_Q2 2022
EDP Form 6 - Trust Fund Utilization Report
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE SECOND QUARTER, CY 2022
Province, City or Municipality: Lucena City
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of | Remarks
[5 empty] | % of | Total Cost | Extentions,
[5 empty] | Completion | Incurred to Date | if any
Supplemental Feeding Program | Various Barangays | 6300000 | 2022-02-14 | 04-24-22 | 100% | 6300000 |  | Completed
Harvesting Machines | Various Barangays | 2500000 | 2017-12-13 | 12-31-18 | 100% | 2069200
Protective Services for People with Disability |  | 3000000 | 05-26-17 | 12-31-18 | 100% | 2789524 |  | Balance returned to DSWD
ECCD F1K | Various Barangays | 1153250 | 2019-02-28 |  | 95.69% | 1103557.7 |  | No target completion date
Fire Code Fees | Bureau of Fire Station | 2091710.14 | 2018-06-30 |  | 96.2% | 2012301.22 |  | No target completion date
Assistance for Don Victor Ville | Brgy. Mayao Kanluran | 12000000 | 2018-08-13 |  | 100% | 12000000 |  | Project Ongoing
Sustainable Livelihood Program | Various Barangays | 5117316 | 2018-12-18 |  | 25.77% | 1318970 |  | No target completion date
Lucena City Promenade by the Bay | Brgy. Talao-talao | 17113228.17 | 2021-10-15 | 2022-07-11 | 80.02% | 14200546.2 |  | Project Ongoing
Concreting of Road | Brgy. Ilayang Dupay | 15000000 |  |  | 0% | 0 |  | Ongoing Settlement
Resettlement Housing Project | Brgy. Ibabang Talim | 21290002 | 2022-03-15 | 2024-03-13 | 0% | 3190622.9 |  | Project Ongoing
Multi-purpose Evacuation Center | Brgy. Mayao Kanluran | 25000000 |  |  | 0% | 0
Improvement of MRF Operations | Brgy. Mayao Kanluran | 150000 |  |  | 0% | 0
We hereby certify that we have reviewed the contents and hereby attest to veracity and correctness of the data or information contained in this document.
(Sgd.) ROSALINA M. CASTILLO |  | (Sgd.) ELLA MICHELLE T. AZAGRA |  |  |  |  | (Sgd.) RODERICK A. ALCALA
City Budget Officer |  | Acting City Accountant |  |  |  |  | City Mayor
Formulas:
Target Completion Date = [Date Started]+270-1